## Sheet1
Stages
Staff
| Planning | Designing | Developing | Testing | Implementing | Total
| (3 weeks) | (10 weeks) | (8 weeks) | (2 weeks) | (1week) | Time
Project Manager
Hours | 12 | 10 | 25 | 20 | 20
Weeks | 3 | 10 | 8 | 1 | 1
Total | 36 | 100 | 200 | 20 | 20 | 376
Database Designer
Hours |  | 5 | 15 | 10 | 20
Weeks |  | 10 | 8 | 1 | 1
Total |  | 50 | 120 | 10 | 20 | 200
Technical Analyst
Hours | 9 | 6 |  | 5
Weeks | 3 | 10 |  | 1
Total | 27 | 60 |  | 5 |  | 92
Systems Analyst
Hours |  | 6 | 6 | 3 | 6
Weeks |  | 10 | 8 | 1 | 2
Total |  | 60 | 48 | 3 | 144 | 255
Graphic Designer
Hours |  |  | 4 | 5
Weeks |  |  | 6 | 1
Total |  |  | 24 | 5 |  | 29
Quality Assurance
Hours | 4 |  |  | 20
Week | 3 |  |  | 2
Total Time | 12 |  |  | 40 |  | 52
Buffer time
Total Time | 75 | 270 | 392 | 83 | 184 | 1004