## Sheet1
Roles | Planning | Analysis | Design | Development | Testing | Deployment | Total
| 3 weeks | 1 week | 2 weeks | 6 weeks | 1 week | 1 week
Hours | 84 | 50 | 185 | 500 | 14 | 10
Project Manager | 32 | 15 | 55 | 155 | 6 | 3 | 266 hours
Project Developer | 30 | 17 | 70 | 167 | 5 | 4 | 293 hours
Database Manager | 22 | 18 | 60 | 178 | 3 | 3 | 284 hours
Total | 84 hours | 50 hours | 185 hours | 500 hours | 14 hours | 10 hours | 843 hours